This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product_Backlog
Product Name:	JADE Manager					Complete Fields in Green!!!
Team ID:	Java Maker

	Team Member Name					Initials	Student ID
Required	Kevin Lopez					K.L.	1001351570

Sprint #	Remaining	Completed This Sprint			Comment
0	33			Total	Total number of features (in column H)
1	29	4		1	Total features left at the end of Sprint #1
2	24	5		2	Total features left at the end of Sprint #2
3	22	2		3	...and so on
4	22	0

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1	13	1	Finished in Sprint 1	Manager	Create a new coffee flavor	Stock and sell coffee products
CC	2	1	5	1	Finished in Sprint 1	Manager	Create a new donut	Stock and sell donuts
GUI	3	1	8	1	Finished in Sprint 1	Manager	Use a main window (GUI) with minimal menu bar only	Reduce training costs	This is the main window, with just a menu bar (for now). For this sprint, you can just hard-code or randomly create java and donuts
PS	4	1	5	1	Finished in Sprint 1	Customer	List the coffee and donut products in a dialog	See what is available (and later, see what the Customer can order)	This is effectively a string stream to a dialog with an OK button
IGUI	5	2	13	2	Finished in Sprint 2	Manager	Use dialogs to create new coffee and donut products	Reduce training costs	One dialog each for coffee and for donuts
BB	6	2	3	2	Finished in Sprint 2	Server	Use a button bar in the main window for common actions	Access features more quickly
CB	7	2	2	2	Finished in Sprint 2	Server	Create a new beloved customer	Keep track of our customers
CO	8	2	8	2	Finished in Sprint 2	Server	Create an order of multiple products	Serve everyone in a customer party
POC	9	2	3	2	Finished in Sprint 2	Customer	Show the servings in an order for the customer (what was ordered / how much it costs)	Verify that my order was taken correctly and see the price	This can simply be text in a MessageDialog, or something snazzier; probably similar to and maybe identical to Feature PS
CSB	10	3	8	3	Finished in Sprint 3	Customer	Associate the order with a customer	Self-order and not have to deal with people	“What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
CE	11	3	13	3	Finished in Sprint 3	Manager	Create a store that stocks items and maintains a cash register	Manage the emporium	This includes item stocks, server and customer lists, and the cash register
MST	12	4	5			Manager	Manage the state of each order (unfilled -> filled and unpaid -> paid,, or unfilled / unpaid -> canceled)	Ensure each order is filled and payment collected
SAVD	13	4	8			Manager	Save all data to a default file on exit or command	Ensure our data isn’t lost
LOAD	14	4	5			Manager	Load data from a default file on startup	Ensure our data isn’t lost
POS	15		5			Server	Show the products in an order for the servers (what to prepare)	Know what to put into each serving in an order	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
PIX	16		21			Customer	Add and display pictures for each item	Better understand the menu
CM	17		3			Owner	Create a new manager	Delegate management tasks to a pro
P&L	18		8			Manager	Add a Profit & Loss statement, showing all income, expenses, and total profit	Ensure that we’re making a profit and thus avoid bankruptcy
RI	19		5			Manager	Display an Inventory Report, listing every item and the quantity in stock	Ensure we don’t run out of any product and thus disappoint our customers
RTM	20		8			Manager	Display a Server Report, listing all info about each server including # of orders served	Better manage our team and reward productive team members
AI	21		8			Server	Restock donuts and coffees	Ensure we can fill every order
RO	22		8			Manager	Create an Order Report, showing all pending orders (unfilled and filled but unpaid)	Better manage our production process
RB	23		5			Manager	Display a Customer Report, listing all info about each customer	Better attract repeat customers and handle complaints
EF	24		8			Manager	Edit a product	Improve our data and keep it synced to reality
ROA	25		3			Manager	Add Order Report option to show completed as well as pending orders	Review our order history seeking patterns to understand how to improve efficiency and profit
SALL	26		5			Owner	Save all data to a specified file	Franchise my company
LALL	27		5			Owner	Load data from a specified file	Franchise my company
CENEW	28		13			Owner	Create a new franchise	Franchise my company
XI	29		21			Manager	Retire a product (no longer enable its selection for a new order, but keep in reports)	Remove items no longer offered from the menu
CS	30					Manager	Hire a NAMED server, and login by server name	Keep track of our employees
ASTO	31					Manager	Also associate a server with the order they fill	Keep track of our employee productivity
XT	32		13			Manager	Suspend a server (no longer allow their selection for an order	Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT	33		5			Manager	Restore a server	Add a former team member tack into service
Product Backlog Burn Chart
Features Remaining at end of Sprint
Sprints

## Sprint_01_Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 30		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 06
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	5
Day 1 Left	0	5
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			Make the base class	Completed Day 1
2			Donut class made	Completed Day 1
3			Java class made	Completed Day 1
4			Store Class made	Completed Day 1
5			Mainwin	Completed Day 1
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_02_Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Nov 06		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 13
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	4
Day 1 Left	0	4
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			Made Customer Class	Completed Day 1
2			Implemented in GUI	Completed Day 1
3			REGEX	Completed Day 1
4			Toolbar	Completed Day 1
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_03_Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Nov 13		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 20
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	3
Day 1 Left	0	3
Day 2 Left	0	0
Day 3 Left	0	0
Day 4 Left	0	0
Day 5 Left	0	0
Day 6 Left	0	0
Day 7 Left	0	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			Create Order Class	Completed Day 1
2			Implement Order Class with Store class	Completed Day 1
3			Set up GUI	Completed Day 1
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days

## Sprint_04_Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 20		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 27
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Tasks
Days